## SMF 1.0
Project Activities & Deliverables | [8 empty] | Amazon Review & Deliverable Dates |  |  |  | Incremental Tasks for Deliverables |  |  |  | Dependencies and Requested Actions
Phase | Project Activity | Assigned to | Project | Project Plan Business Reason | Project Activity Start Date | Project Activity End Date | Deliverable | Status | Amazon Review Start Date | Amazon Review Dates | Amazon Review End Date | Amazon Deliverable Due Date | Deliverable Sub Task Number | Deliverable Sub Task Creation Date | Deliverable Sub Task | Deliverable Sub Task Due Date | Dependency | Comments and Action requested | Assigned | Required Completion Date for Schedule | Why the request is being made
Discovery | Requirements Validation | Siva | SMF 1.0 | SmartForm application access needs to be restricted to a subset of Amazon employees | 2019-02-13 | 2019-02-19 | SmartForm Authentication | Pending | Amazon/LTI Working Sessions for Requirements Questions & Clarifications 2/11/2019 to 2/19/2019 |  |  | 2019-02-19 | 1 | 2019-02-11 | Determine Authentication Methodology | 2019-02-15 | Amazon | Determine authorization Identity Provider for SmartForm Provide instruction for the use of the identity provider | KJ Davis | 2019-02-15 | Not all users can have access to SmartForm and an identity source is required to/prevent allow access.
Discovery | Requirements Validation | Siva Varun | SMF 1.0 | Display correct screens and transactions for an employee based on persona, supervisor status, region, and location. | 2019-02-13 | 2019-02-19 | Validate Business Rules for Authorization | Pending |  |  |  | 2019-02-19 | 1 | 2019-02-11 | Persona identification and mapping | 2019-02-15 | Amazon | Information to map personas to ESS, GSS, and MSS groupings. | KJ Davis | 2019-02-15 | Rules to display the correct transactions and functions based on Persona in SmartForm
Discovery | Requirements Validation | Satish Mohan | SMF 1.0 | Reporting details for user activity, bot processing, errors, and transactions defined to the most detailed level. | 2019-02-13 | 2019-02-19 | Transaction Monitoring and Reporting | Pending |  |  |  | 2019-02-19 | 1 | 2019-02-11 | Queries to extract data for reports | 2019-02-15 | Amazon | Amazon to provide additional details for the reports Audit Trail Reporting, Compliance report, Operation report, Ticketing Detail Report, Project Success Metrics 15th Feb 2019 - Working of query preparations | Abhi | 2019-02-15 | In order to produce the reports the expected output of the report needs to be defined. The precise events for the transactions that need capture must be known in order to store the information and report it. This may also have an impact on design
Discovery | Requirements Validation | Varun Mayuresh Koteswararao Balanaresh | SMF 1.0 | Matrix of personas, regions, locations, and exception handling for all transactions | 2019-02-13 | 2019-02-19 | Validate Business Rules for Transactions | WIP |  |  |  | 2019-02-19 | 1 | 2019-02-11 | Exception for rules by country, location, Role/Persona Privileges | 2019-02-15 | None | Technical Support to complete FRD based on user stories Varun identifies the requirements in the story and Mayuresh, Koteswararao, & Balanaresh research and provide a technical input for FRD. 14th Feb 2019 - working on 'How to incorporate approval process for transaction in the Smart Form setup |  | 2019-02-15
Discovery | Requirements Validation | Varun Mayuresh Koteswararao Balanaresh | SMF 1.0 | Ensure the User Stories represent all transactions/functions to be tested and the details are well defined. | 2019-02-13 | 2019-02-19 | User Story Validation | WIP |  |  |  | 2019-02-19 | 1 | 2019-02-11 | Completed the validation of user stories | 2019-02-17 | Working Session | Varun is confirming with Abhi but has no outstanding questions 14th Feb 2019 - 61 user stories complete and 10 are pending (Varun) 15th Feb 2019 - Varun has few queries on user stories which he will be clarifying in the next session | Abhi | 2019-02-17
Discovery | Requirements Validation | Sugur Shivam | SMF 1.0 | Amazon Design & Branding Standards | 2019-02-13 | 2019-02-19 | Amazon Design & Branding Standards for UX/UI | Pending |  |  |  | 2019-02-19 | 1 | 2019-02-11 | Visual Design Standards | 2019-02-15 | Amazon | Require Visual Design Standards to begin UI Design Branding Guidelines Style Guidelines 14th Feb 2019 - Demo for Wireframes completed till HR persona and action covered till Others | Abhi | 2019-02-15 | Achieve the proper design standards
Design | Solution Design | Purushothaman Sivasankar | SMF 1.0 | Creation of the Worklist's underlying table structure and relationship to the data set to be processed by the bots | 2019-02-20 | 2019-03-05 | Work List structure Validate Data Structure and required Data | WIP | 2019-02-20 |  | 2019-03-05 | 2019-03-05 | 1 | 2019-02-11 | Identifying the required fields Fields, data types, and relationships, acceptable values | 2019-03-05 | Amazon | No dependency from Amazon at this time. This task links to the Automation Database where the bots get the work. The worklist is the specific request of the bot to do work and the automation database contains the work to be performed. Amazon will need to confirm to architecture 14th Feb 2019 - Team is working on it. Work is still in progress
Design | Requirements Validation | Siva Mayuresh Santosh | SMF 1.0 | Underlying table structure of Smartform to support the Functional Requirements | 2019-02-20 | 2019-02-19 | Smartform Validate Data Structure and required Data | WIP | 2019-02-20 |  | 2019-03-05 | 2019-03-05 | 1 | 2019-02-11 | Identifying the required fields Fields, data types, and relationships, acceptable values | 2019-03-05 | None | 14th Feb 2019 - Data Structure for Master Table and Transactions are ready. Need validation from DBA side 15th Feb 2019 - Working on changes suggested in checklist call
Design | Design | Sugur Shivam | SMF 1.0 | Create Wireframes SmartForm Screens | 2019-02-20 | 2019-03-05 | Wireframe | WIP | 2019-02-20 |  | 2019-03-05 | 2019-03-05 | 1 | 2019-02-11 |  | 2019-03-05 | Select Dependency | 15th Feb 2019 - Working on option 2
Design | Design | Varun | SMF 1.0 | Functions of SmartForm | 2019-02-20 | 2019-03-05 | FSD | WIP | 2019-02-20 |  | 2019-03-05 | 2019-03-05 | 1 | 2019-02-11 |  | 2019-03-05 | Select Dependency
Design | Design | Siva Mayuresh Koteswararao | SMF 1.0 | Overall Solution Planning and Design | 2019-02-20 | 2019-03-05 | SDD | WIP | 2019-02-20 |  | 2019-03-05 | 2019-03-05 | 1 | 2019-02-11 | Case Management & Remedy APIs | 2019-03-05 | Amazon | Define existing services and provide guidance 14th Feb 2019 - Flow diagrams are ready for Integration part and for UI level Flow diagram work is in progress 15th Feb 2019 - Working on changes suggested in internal call | KJ Davis | 2019-02-15 | Ticket sand cases are part of the overall Solution Design
Design | Design | Siva Mayuresh Koteswararao | SMF 1.0 | Database & Tables for SmartForm | 2019-02-20 | 2019-03-05 | SDD | WIP | 2019-02-20 |  | 2019-03-05 | 2019-03-05 | 2 | 2019-02-11 | Define Validation Rules | 2019-03-05 | Amazon | Confirm the values to be used for employees and transactions 14th Feb 2019 - Data Structure diagram is ready 15th Feb 2019 - Working on changes suggested in internal call | KJ Davis | 2019-02-15 | Validation rules are a key component of the new solution to reduce errors.
Design | Design | Siva Mayuresh Koteswararao | SMF 1.0 | Services for Worklist and Automation Database | 2019-02-20 | 2019-03-05 | SDD | WIP | 2019-02-20 |  | 2019-03-05 | 2019-03-05 | 3 | 2019-02-11 | Apes and Web Services | 2019-03-05 | Amazon | Confirm Platform and RESTful API capability 14th Feb 2019 - Work in progress 15th Feb 2019 - Data Structure architecture presented in internal call. Got few suggestions and working on that | KJ Davis | 2019-02-16 | Services are required for the communication between the components.
Design | Design | Ken Bowers | SMF 1.0 | Project Plan for SMF 1.0 | 2019-02-20 | 2019-03-05 | Project Plan | WIP | 2019-02-20 |  | 2019-03-05 | 2019-03-05 | 1 | 2019-02-11 |  | 2019-03-05 | None
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | [9 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | [9 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable | [9 empty] | Select Dependency
Select Phase | Select Activity |  | Select Project |  |  |  | Select Deliverable

## DM 3.0
Project Deliverables and Tasks | [7 empty] | Amazon Review & Deliverable Dates |  |  |  | Incremental Tasks for Deliverables |  |  |  | Dependencies and Requested Actions
Phase | Assigned to | Project | Project Plan Business Reason | Project Activity Start Date | Project Activity End Date | Deliverable | Status | Amazon Review Start Date | Amazon Review Dates | Amazon Review End Date | Amazon Deliverable Due Date | Deliverable Sub Task Number | Deliverable Sub Task Creation Date | Deliverable Sub Task | Deliverable Sub Task Due Date | Dependency | Comments and Action requested | Assigned | Required Completion Date for Schedule | Why the request is being made
Discovery | Ashok Prashansa | DM 3.0 | Obtain complete details of the existing process including process variations and exceptions. Click by Click screenshots are a required component | 2019-02-13 | 2019-02-19 | PDD | Closed | Amazon/LTI Working Sessions for Requirements Questions & Clarifications 2/11/2019 to 2/19/2019 |  |  | 2019-02-19 | 1 | 2019-02-11 | Add Clickstream to PDD | 2019-02-15 | Amazon | Provide Click by Click screen shots of the activities RPA needs to automate | Anand | 2019-02-08 | Clickstreams were received - Closed
Discovery | Ashok Prashansa Sivasankar | DM 3.0 | Obtain complete details of the existing process including process variations and exceptions. Click by Click screenshots are a required component | 2019-02-13 | 2019-02-19 | PDD | WIP |  |  |  | 2019-02-19 | 2 | 2019-02-11 | Exception Handling Detailed Process Flow | 2019-02-15 | None
Discovery | Ashok Sivasankar | DM 3.0 | Process Automation Frequency - The bots run on a schedule and it is vital to understand how often they will perform a task. Both the user experience and system impact are considerations in creating the schedule | 2019-02-13 | 2019-02-19 | PDD | WIP |  |  |  | 2019-02-19 | 3 | 2019-02-11 | Process Automation Frequency | 2019-02-15 | Amazon | Ashok added queries to the tracker and will be reviewed with Abhi 2/13/2019. |  | 2019-02-15 | Process Automation Frequency - The bots run on a schedule and it vital to understand how often they will perform a task. Both the user experience and system impact are considerations in creating the schedule
Discovery | Ashok Sivasankar | DM 3.0 | Credential Lifecyle & Maintenance for Bots | 2019-02-13 | 2019-02-19 | PDD | Pending |  |  |  | 2019-02-19 | 4 | 2019-02-11 | Credential Lifecyle & Maintenance for Bots How are they requested? How long is a password set for? How is a password reset? What is the support group for the credentials? | 2019-02-15 | Amazon | The process of receiving and maintaining bot credentials is critical for operations. |  | 2019-02-15 | Bots require credentials that follow a Lifecyle similar to users and require maintenance and support
Design | Ashok Sivasankar | DM 3.0 | Complete Process flow for RPA All the possible flows for a transaction and the interactions with solution components, PeopleSoft, Remedy, SmartForm, Automation Database and Worklist | 2019-02-20 | 2019-03-05 | SDD | Pending | 2019-02-20 |  | 2019-03-05 | 2019-03-05 | 1 | 2019-02-11 | High Level Diagram Components Determine Process Variations Includes Exception Handling Notification | 2019-02-15 | Amazon | Details are required for table structure for Fake Self Service rules to process the records | Abhi | 2019-02-15 | There is an existing process that requires some replication and modification. The details of the existing process are required to replicate it.
Design | Varun | DM 3.0 | Functional Specifications for Automations | 2019-02-20 | 2019-03-05 | FDD | WIP | 2019-02-20 |  | 2019-03-05 | 2019-03-05 | 1 | 2019-02-11 |  |  | Select Dependency
Design | Mahesh | DM 3.0 | Technical Specifications for Automations | 2019-02-20 | 2019-03-05 | TDD | WIP | 2019-02-20 |  | 2019-03-05 | 2019-03-05 | 1 | 2019-02-11 |  |  | Select Dependency
Design | Ken Bowers | DM 3.0 | Project Plan for DM 3.0 | 2019-02-20 | 2019-03-05 | Project Plan | WIP | 2019-02-20 |  | 2019-03-05 | 2019-03-05 | 1 | 2019-02-11 |  |  | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP | [8 empty] | Select Dependency
Select Phase |  | Select Project |  |  |  | Select Deliverable | WIP