## Estimates
| Digital | RPA
Total Efforts In Days | 948
Total Efforts In Weeks | 189.6
Total No. High PODs | 5.51

## Digital Tasks
All Efforts are in Days
Sr No | Service Name | Integration Efforts | UI Activities | UI Effort | UX Activities | UX Effort | DB Activities | Database | Assumptions
1 | Read Flat File Service |  |  | NA |  | NA |  |  | 9 tables
| Create Tables | [5 empty] | Create Tables | 1
| Create Service to read Flat files | [5 empty] | Create Index's / partoition / Materilized Views | 1
| Create Batch Job | 4 |  |  |  |  | Finetuning queries | 2
| Create JSON Classes | 1 |  |  |  |  | Improve performance | 2
| Create POJO Classes | 1
| Create Model Classes | 1
| Create Service Classes | 1
| Create Transformation Classes | 1
| Create Exception Handling Classes | 1
| Create Logging Classes | 1
| Create Utility Classes | 1
| Create Configuration files | 1
| Create Client to consume 3rd party API | 1
| Write Junit Test Cases | 6
2 | Create Remedy Ticket Service |  |  | NA |  | NA
Create Service to rise a ticket
| Create JSON Classes | 0.5
| Create POJO Classes | 0.5
| Create Controller Classes | 0.5
| Create Model Classes | 0.5
| Create Service Classes | 0.5
| Create Transformation Classes | 0.5
| Create Exception Handling Classes | 0.5
| Create Logging Classes | 0.5
| Create Utility Classes | 0.5
| Create Configuration files | 0.5
| Create Client to consume 3rd party API | 1
| Write Junit Test Cases | 2
3 | Smart Form Service | [7 empty] | 49 Transaction (8 self-services)
| Create JSON Classes | 15 | HTML Template creation | 30 | Wireframe Prototyping | 5 | Create Tables | 10
| Create POJO Classes | 15 | Browser compatibility | 16 | Paper Prototype | 5 | Create Index's | 5
| Create Controller Classes | 30 | Responsive web design | 14 | Prepare Basic Sketch (Low fidelity Wireframe) | 5
| Create Model Classes | 30 | Services/Models |  | Visual Design creation | 5
| Create Service Classes | 30 | HTTP requests success and fail messages | 30
| Create Transformation Classes | 30 | Consuming APIs based on roles and country | 30
| Create Exception Handling Classes | 10 | Handling error handling through modals/popups | 30
| Create Logging Classes | 10 | Data deliver to Integration team | 40
| Create Utility Classes | 10 | Unit Testing | 50
| Create Configuration files | 10
| Create Client to consume 3rd party API | 20
| Write Junit Test Cases | 40
4 | Configuration / Admin Service
| Create JSON Classes | 0.5 | HTML Template creation | 2 | Wireframe Prototyping | 0.5 | Create Tables | 3
| Create POJO Classes | 0.5 | Browser compatibility | 0.5 | Paper Prototype | 0.5 | Create Index's | 2
| Create Controller Classes | 1 | Responsive web design | 0.5 | Prepare Basic Sketch (Low fidelity Wireframe) | 0.5
| Create Model Classes | 1 | Services/Models |  | Visual Design creation | 0.5
| Create Service Classes | 1 | HTTP requests success and fail messages | 0.5
| Create Transformation Classes | 0.5 | Consuming APIs based on roles and country | 0.5
| Create Exception Handling Classes | 0.5 | Handling error handling through modals/popups | 0.5
| Create Logging Classes | 0.5 | Data deliver to Integration team | 0.5
| Create Utility Classes | 0.5 | Unit Testing | 1
| Create Configuration files | 1
| Write Junit Test Cases | 3
5 | Notification Service |  |  | NA |  | NA |  |  | If we use 3rd Party API
| Create JSON Classes | 0.5
| Create POJO Classes | 0.5
| Create Controller Classes | 0.5
| Create Model Classes | 0.5
| Create Service Classes | 0.5
| Create Transformation Classes | 0.5
| Create Exception Handling Classes | 0.5
| Create Logging Classes | 0.5
| Create Utility Classes | 0.5
| Create Configuration files | 0.5
| Create Client to consume 3rd party API | 1
| Write Junit Test Cases | 2
6 | Landing page
| Create JSON Classes | 0.5 | HTML Template creation | 3 | Wireframe Prototyping | 1 | Write queries | 2
| Create POJO Classes | 0.5 | Browser compatibility | 1 | Paper Prototype | 1 | Finetuning queries | 2
| Create Controller Classes | 0.5 | Responsive web design | 1 | Prepare Basic Sketch (Low fidelity Wireframe) | 1 | Improve performance | 1
| Create Model Classes | 0.5 | Services/Models |  | Visual Design creation | 2
| Create Service Classes | 0.5 | HTTP requests success and fail messages | 2
| Create Transformation Classes | 0.5 | Consuming APIs based on roles and country | 2
| Create Exception Handling Classes | 0.5 | Handling error handling through modals/popups | 1
| Create Logging Classes | 0.5 | Data deliver to Integration team | 2
| Create Utility Classes | 0.5 | Unit Testing | 3
| Create Configuration files | 0.5
| Write Junit Test Cases | 1
7 | Reports | NA |  | NA |  | NA
[7 empty] | Write queries | 2
[7 empty] | Finetuning queries | 1
[7 empty] | Improve performance | 1
8 | Rules Engine Service
| Create JSON Classes | 1
| Create POJO Classes | 1
| Create Controller Classes | 1
| Create Model Classes | 1
| Create Service Classes | 1
| Create Business Rules | 2
| Create Transformation Classes | 1
| Create Exception Handling Classes | 1
| Create Logging Classes | 1
| Create Utility Classes | 1
| Create Configuration files | 1
| Create Client to consume 3rd party API | 1
| Write Junit Test Cases | 3
9 | RPA Service
| Create JSON Classes | 1
| Create POJO Classes | 1
| Create Controller Classes | 1
| Create Model Classes | 1
| Create Service Classes | 1
| Create Business Rules | 2
| Create Transformation Classes | 1
| Create Exception Handling Classes | 1
| Create Logging Classes | 1
| Create Utility Classes | 1
| Create Configuration files | 1
| Create Client to consume 3rd party API | 1
| Write Junit Test Cases | 2
10 | Work List Services
| Create JSON Classes | 3 |  |  |  |  | Write queries | 2
| Create POJO Classes | 3 |  |  |  |  | Finetuning queries | 2
| Create Controller Classes | 3 |  |  |  |  | Improve performance | 1
| Create Model Classes | 3
| Create Service Classes | 3
| Create Transformation Classes | 3
| Create Exception Handling Classes | 3
| Create Logging Classes | 3
| Create Utility Classes | 3
| Create Configuration files | 3
| Create Client to consume 3rd party API | 5
| Write Junit Test Cases | 15
| (DEV + UT) Efforts | 383 |  | 261 |  | 27 |  | 40
| QA Efforts (IT, Function & Performance) | 19.15 |  | 104.4 |  | 10.8 |  | 16
| Buffer | 40.215 |  | 36.54 |  | 3.78 |  | 5.6
| Total Efforts | 442 |  | 402 |  | 42 |  | 62
Need more clarity on below points for estimates
1 | Approval process
2 | Work Flow Engine Service
3 | SSO Service

## Process
Process Scan ID | Hub | Service Area | Process (level 1) | Region/countries supported | Purpose of the process | Digital - Tasks / Services | RPA - Tasks / Services
411, 413, 414, 415, 416, 417, 418, 419, 420 | India | Data Management | Job Data Changes | Americas | Data Entry - upload Department/Product Line changes in PS | Read Flat File Service Create Remedy Ticket Service Data Management Service Configuration / Admin Service Notification Service SSO Service Dashboard / Landing page Reports Work List Services
402 | India | Data Management | Job Data Changes | Americas | Data Entry - To update Dept changes in PS. Requests are also Submitted through PeopleSoft Manager Self-Service | Read Flat File Service Create Remedy Ticket Service Data Management Service Configuration / Admin Service Notification Service SSO Service Dashboard / Landing page Reports Work List Services
400 | India | Data Management | Job Data Changes | Americas | Data Entry - To update Business Title changes in PS. Requests are also Submitted through PeopleSoft Manager Self-Service | Read Flat File Service Create Remedy Ticket Service Data Management Service Configuration / Admin Service Notification Service SSO Service Dashboard / Landing page Reports Work List Services
412 | India | Data Management | Job Data Changes | Americas | Data Entry - upload business title changes in PS | Read Flat File Service Create Remedy Ticket Service Data Management Service Configuration / Admin Service Notification Service SSO Service Dashboard / Landing page Reports Work List Services

## POD Metadata
| POD Complexity | Duration inWeeks | Resources | BA | UX | DB | UI | Integration | QA | Weekly Price
Digital | Medium | 6 | 3.3 |  | 0.3 | 0.5 | 1 | 0.5 | 1 | 5424
| High | 8 | 4.3 |  | 0.3 | 1 | 1 | 1 | 1 | 6440
| Very High | 9 | 5.3 |  | 0.3 | 1 | 1 | 2 | 1 | 7480
| POD Complexity | Duration inWeeks | Resources | BA |  |  |  | Integration | QA | Weekly Price
RPA | Medium | 8 | 2.4 |  |  |  |  | 1.4 | 1 | 4100
| High | 12 | 3.3 |  |  |  |  | 2.3 | 1 | 5020
| Very High | 16 | 4.75 |  |  |  |  | 3.75 | 1 | 6870