## Sheet1
Task Name | Duration | Start | Finish | Predecessors | Role | Resource Names | Project Phase
SmartForm 1.0 - 1.1 | 88d | Fri 2/8/19 | Tue 6/11/19
SmartForm 1.0 - 1.1 including Warranty and Closure | 88d | Fri 2/8/19 | Tue 6/11/19
SmartForm 1.0 - 1.1 Discovery thru Go Live | 77d | Fri 2/8/19 | Mon 5/27/19
SmartForm 1.0 Discovery thru User Acceptance Testing | 70d | Fri 2/8/19 | Thu 5/16/19
Discovery Package Receipt & Hand Off | 3d | Fri 2/8/19 | Tue 2/12/19
Receive Amazon Discover Package (ADP) | 1d | Fri 2/8/19 | Fri 2/8/19
Amazon walk-through of ADP | 2d | Mon 2/11/19 | Tue 2/12/19 | 6 | Business Analyst | Abhi | III. Discovery
Requirements Validation* | 5d | Wed 2/13/19 | Tue 2/19/19 | 7 | Business Analyst | Abhi | III. Discovery
Project Plan Estimation does not include Work List, SSO, Reports, or Approval Workflow recently disclosed to LTI | 5d | Wed 2/13/19 | Tue 2/19/19 |  | Digital PM | Mohan | III. Discovery
LTI Reviews ADP and Raises Queries based on Development Area | 5d | Wed 2/13/19 | Tue 2/19/19 |  | Digital PM | Mohan | III. Discovery
Process Flows & Functional Requirements | 5d | Wed 2/13/19 | Tue 2/19/19 |  | Business Analyst | Varun/Mohan | III. Discovery
Nonfunctional Requirements | 5d | Wed 2/13/19 | Tue 2/19/19 |  | Business Analyst | Varun/Mohan | III. Discovery
Exception - Error Handling Requirements | 5d | Wed 2/13/19 | Tue 2/19/19 |  | Business Analyst | Varun/Mohan | III. Discovery
Confirm User Stories | 5d | Wed 2/13/19 | Tue 2/19/19 |  | APS Manager / HRS Manager | Kellmesa | III. Discovery
UX Requirements | 5d | Wed 2/13/19 | Tue 2/19/19 |  | UX Lead | Naganna S. Sugur | III. Discovery
UI Requirements | 5d | Wed 2/13/19 | Tue 2/19/19 |  | UI Lead | Koteswararao | III. Discovery
Data Sources - Database | 5d | Wed 2/13/19 | Tue 2/19/19 |  | Database Lead | LTI | III. Discovery
System Integration - Web Services & APIs | 5d | Wed 2/13/19 | Tue 2/19/19 |  | Integration Lead | Mayuresh/Santosh/Varun | III. Discovery
DESIGN | 10d | Wed 2/20/19 | Tue 3/5/19
High Level Design | 10d | Wed 2/20/19 | Tue 3/5/19 | 8
LTI Deliverables for Requirement Validation & High Level Solution Design | 10d | Wed 2/20/19 | Tue 3/5/19 |  | Development Lead | Siva/Mayuresh/Koteswararao | IV. Design
Create Functional Design Requirements (FRD) | 10d | Wed 2/20/19 | Tue 3/5/19 |  | Business Analyst | Varun/Mohan | IV. Design
Create Wireframes | 10d | Wed 2/20/19 | Tue 3/5/19 |  | UX Lead | Sugur/Shivam | IV. Design
Create Solution Design Document | 10d | Wed 2/20/19 | Tue 3/5/19 |  | Integration Lead | Mayuresh/Santosh/Varun | IV. Design
Revalidation of the Project Plan | 10d | Wed 2/20/19 | Tue 3/5/19 |  | Digital PM/Project PM | Mohan/Ken | IV. Design
LTI Walk through of High Level Solution Design by Lead (multiple iterations) | 10d | Wed 2/20/19 | Tue 3/5/19 |  | Development Leads | Siva/Mayuresh/Koteswararao | IV. Design
Database Design | 10d | Wed 2/20/19 | Tue 3/5/19 |  |  |  | IV. Design
Determine Data Requirements | 10d | Wed 2/20/19 | Tue 3/5/19 |  | DBA | Amresh | IV. Design
Determine Data Sources | 10d | Wed 2/20/19 | Tue 3/5/19 |  | DBA | Amresh | IV. Design
Schema and Tables | 10d | Wed 2/20/19 | Tue 3/5/19 |  | DBA | Amresh | IV. Design
Feature Highlights in HLD | 10d | Wed 2/20/19 | Tue 3/5/19 |  | Development Leads | Siva/Mayuresh/Koteswararao | IV. Design
Redirect to Self Service Portal (SMF 1.0) | 10d | Wed 2/20/19 | Tue 3/5/19 |  | Development Leads | Siva/Mayuresh/Koteswararao | IV. Design
SMF - Pick Transaction - User and Transaction Rules - Redirect PP | 10d | Wed 2/20/19 | Tue 3/5/19 |  | Development Leads | Varun/Mayuresh/Mohan/Ken | IV. Design
Personal Details - Self Service | 10d | Wed 2/20/19 | Tue 3/5/19 |  | Development Leads | Varun/Mayuresh/Mohan/Ken | IV. Design
Address - Contact Details - Disability - Emergency Contact - Ethnicity - Gender - Preferred Name - Vetran info | 10d | Wed 2/20/19 | Tue 3/5/19 |  | Development Leads | Varun/Mayuresh/Mohan/Ken | IV. Design
Job Data - Self Service | 10d | Wed 2/20/19 | Tue 3/5/19 |  | Development Leads | Varun/Mayuresh/Mohan/Ken | IV. Design
Business Title - Company - Department - FCLM Area and FCLM job - Full Time - Part Time - Pay Group - Product Line - Shift Pattern and ADP shift - Supervisor Change - Transfer | 10d | Wed 2/20/19 | Tue 3/5/19 |  | Development Leads | Varun/Mayuresh/Mohan/Ken | IV. Design
No Self Service (SMF 1.1) - Structured Input & Ticket Creation | 10d | Wed 2/20/19 | Tue 3/5/19 |  | Development Leads | Siva/Mayuresh/Koteswararao | IV. Design
SMF - Pick Transaction - User and Transaction Rules - Create Ticket | 0d | Wed 2/20/19 | Wed 2/20/19 |  | Business Analyst | Varun/Mohan | IV. Design
Personal Details -Individual Only | 10d | Wed 2/20/19 | Tue 3/5/19 |  | Development Leads | Varun/Mayuresh/Mohan/Ken | IV. Design
Legal Name - SSN - SIN - National ID - CRI National ID | 10d | Wed 2/20/19 | Tue 3/5/19 |  | Business Analyst | Varun/Mohan | IV. Design
Personal Details - Individual or Bulk | 10d | Wed 2/20/19 | Tue 3/5/19 |  | Development Leads | Varun/Mayuresh/Mohan/Ken | IV. Design
Address - Contact Details - Disability - Emergency Contact - Work Permit Details - Ethinicity - Gender - Preferred Name - Veteran Info - Educational qualification - Date of Birth - Visual Survey Conducted - Bank Account Number - Bank Account details | 10d | Wed 2/20/19 | Tue 3/5/19 |  | Business Analyst | Varun/Mohan | IV. Design
Job Data - Individual Only | 10d | Wed 2/20/19 | Tue 3/5/19 |  | Business Analyst | Varun/Mohan | IV. Design
Amazon Discount Code - Business Unit Change - CORP Addendum - EA Changes - Eligibility - Ops Addendum - Part time Work Arrangement- FWA - Public Transportation Reimbursement - Suspension - Telecommuting-Individual | 10d | Wed 2/20/19 | Tue 3/5/19 |  | Business Analyst | Varun/Mohan | IV. Design
Job Data - Individual or Mass | 10d | Wed 2/20/19 | Tue 3/5/19 |  | Business Analyst | Varun/Mohan | IV. Design
Agency - Business title - Company - Compensation - Department - Employment Date - FCLM Area and FCLM job - Full time - Part Time - Job Code - Location - M&A Hire - Re-Hire - Office Location Change - Pay group - Pay rate - Product Line - Promotions - Seas | 10d | Wed 2/20/19 | Tue 3/5/19 |  | Business Analyst | Varun/Mohan | IV. Design
Configurable Screens and Exceptions | 10d | Wed 2/20/19 | Tue 3/5/19 |  | Business Analyst | Varun/Mohan | IV. Design
Configurable Screens and Exceptions | 10d | Wed 2/20/19 | Tue 3/5/19 |  | Development Leads | Siva/Mayuresh/Koteswararao | IV. Design
Ability of an Administrator to remove or add Self Service Transactions in Smartform | 10d | Wed 2/20/19 | Tue 3/5/19 |  | Development Leads | Siva/Mayuresh/Koteswararao | IV. Design
Escape Valve | 10d | Wed 2/20/19 | Tue 3/5/19 |  | Development Leads | Siva/Mayuresh/Koteswararao | IV. Design
At any time there would be Escape Valve depending on request for the requester inside a smart form. Which could generate a ticket out using quick link or WFA API depending upon type of request. | 10d | Wed 2/20/19 | Tue 3/5/19 |  | Development Leads | Siva/Mayuresh/Koteswararao | IV. Design
Escape Valve should capture the reason within smart form on why the requester need to generate a ticket before generating the ticket. Reason can be stored and easily reportable if need to be | 10d | Wed 2/20/19 | Tue 3/5/19 |  | Development Leads | Siva/Mayuresh/Koteswararao | IV. Design
My request does not fall in any category - Request is for someone who is not active employee - Portal is not supporting my attachment for mass update | 10d | Wed 2/20/19 | Tue 3/5/19 |  | Development Leads | Siva/Mayuresh/Koteswararao | IV. Design
Agile High Level Design Activities | 10d | Wed 2/20/19 | Tue 3/5/19 |  | PMs and Leads | Mohan/Ken | IV. Design
UX - UI High Level Design | 10d | Wed 2/20/19 | Tue 3/5/19 |  | UI/UX Leads | Koteswararao/Sugur | IV. Design
Wireframe Prototyping | 10d | Wed 2/20/19 | Tue 3/5/19 |  | UI/UX Leads | Koteswararao/Sugur | IV. Design
Paper Prototype | 10d | Wed 2/20/19 | Tue 3/5/19 |  | UI/UX Leads | Koteswararao/Sugur | IV. Design
Prepare Basic Sketch (Low fidelity Wireframe) | 10d | Wed 2/20/19 | Tue 3/5/19 |  | UI/UX Leads | Koteswararao/Sugur | IV. Design
Visual Design creation | 10d | Wed 2/20/19 | Tue 3/5/19 |  | UI/UX Leads | Koteswararao/Sugur | IV. Design
HL Design Review - Amazon | 10d | Wed 2/20/19 | Tue 3/5/19 |  | Product/Business/Technical | Abhi/Anand/? | IV. Design
Business Line Review | 10d | Wed 2/20/19 | Tue 3/5/19 |  | Product/Business Analyst | Abhi/Anand | IV. Design
Technical Review | 10d | Wed 2/20/19 | Tue 3/5/19 |  | UX Review/Visual Design | Malissa/Abhi to provide | IV. Design
UX - UI Standards | 10d | Wed 2/20/19 | Tue 3/5/19 |  | Amazon UX Reviewer | TBD | IV. Design
Visual Design | 10d | Wed 2/20/19 | Tue 3/5/19 |  | Amazon Style & Standards | TBD | IV. Design
Amazon's Sign Off on FSD, SDD, and Revised Project Plan | 1d | Wed 3/6/19 | Wed 3/6/19 | 26 | Validation Complete |  | IV. Design
Infrastructure & Access Readiness | 51d | Fri 2/8/19 | Fri 4/19/19 |  |  |  | V. Build
Sprint Zero - Setup DEV/LTI Access/Onboarding/Case API Readiness | 19d | Fri 2/8/19 | Wed 3/6/19
Access Readiness | 19d | Fri 2/8/19 | Wed 3/6/19 |  |  |  | V. Build
LTI Onboarding | 16d | Fri 2/8/19 | Fri 3/1/19 |  |  |  | V. Build
Submit background check request | 1d | Fri 2/8/19 | Fri 2/8/19 |  | Contract Management | Rajnish Batra | V. Build
Submit PS onboarding request | 1d | Fri 2/8/19 | Fri 2/8/19 |  | Contract Management | Rajnish Batra | V. Build
Laptop to LTI users | 15d | Mon 2/11/19 | Fri 3/1/19 | 71,72 | Amazon Provisioning | KJ Davis | V. Build
LTI Access | 3d | Mon 3/4/19 | Wed 3/6/19 |  |  |  | V. Build
VDI access (If required) | 1d | Mon 3/4/19 | Mon 3/4/19 | 73 | Amazon Provisioning | KJ Davis | V. Build
VDI Connectivity test | 1d | Tue 3/5/19 | Tue 3/5/19 | 75 | LTI Resources | Mohan/Ashok | V. Build
Application access (dev & test environment) | 1d | Wed 3/6/19 | Wed 3/6/19 | 76 | LTI Resources | Mohan/Ashok | V. Build
Shared drive access | 1d | Mon 3/4/19 | Mon 3/4/19 | 73 | LTI Resources | Mohan/Ashok | V. Build
Developer Tools Training | 3d | Mon 3/4/19 | Wed 3/6/19 | 73 | LTI Resources | Mohan/Ashok | V. Build
Case Management API Readiness | 1d | Fri 2/8/19 | Fri 2/8/19 |  | HRSS - APS | krangard/KJ Davis
Understand and Test Case APIs | 1d | Fri 2/8/19 | Fri 2/8/19
Infrastructure Readiness | 19d | Fri 2/8/19 | Wed 3/6/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Infrastructure - Setup - Dev | 19d | Fri 2/8/19 | Wed 3/6/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
UI - UX Development Requirements | 19d | Fri 2/8/19 | Wed 3/6/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Visual Studio Code | 19d | Fri 2/8/19 | Wed 3/6/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Node.js | 19d | Fri 2/8/19 | Wed 3/6/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Angular 6, Karma & Jasmin | 19d | Fri 2/8/19 | Wed 3/6/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
SVN /GitHub | 19d | Fri 2/8/19 | Wed 3/6/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Bootstrap | 19d | Fri 2/8/19 | Wed 3/6/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Integration Development | 19d | Fri 2/8/19 | Wed 3/6/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Common Services Development Requirements | 19d | Fri 2/8/19 | Wed 3/6/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Postman | 19d | Fri 2/8/19 | Wed 3/6/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
SOAP UI | 19d | Fri 2/8/19 | Wed 3/6/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Integration Development Requirements | 19d | Fri 2/8/19 | Wed 3/6/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Java 1.8 | 19d | Fri 2/8/19 | Wed 3/6/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Spring 5.x | 19d | Fri 2/8/19 | Wed 3/6/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Hibernate 4.X | 19d | Fri 2/8/19 | Wed 3/6/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Soap UI | 19d | Fri 2/8/19 | Wed 3/6/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Junit | 19d | Fri 2/8/19 | Wed 3/6/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Maven | 19d | Fri 2/8/19 | Wed 3/6/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Jboss | 19d | Fri 2/8/19 | Wed 3/6/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Eclipse Neon | 19d | Fri 2/8/19 | Wed 3/6/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
SonarQube | 19d | Fri 2/8/19 | Wed 3/6/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
SVN /GitHub | 19d | Fri 2/8/19 | Wed 3/6/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Database Infrastructure - MySQL | 19d | Fri 2/8/19 | Wed 3/6/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Data Model creation | 19d | Fri 2/8/19 | Wed 3/6/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Database Design | 19d | Fri 2/8/19 | Wed 3/6/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Database Design Review | 19d | Fri 2/8/19 | Wed 3/6/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
DDL & DML Creation | 19d | Fri 2/8/19 | Wed 3/6/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
DDL & DML Review | 19d | Fri 2/8/19 | Wed 3/6/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Infrastructure - Setup - QA | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
UI - UX Development Requirements | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Visual Studio Code | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Node.js | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Angular 6, Karma & Jasmin | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
SVN /GitHub | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Bootstrap | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Integration Development | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Common Services Development Requirements | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Postman | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
SOAP UI | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Integration Development Requirements | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Java 1.8 | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Spring 5.x | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Hibernate 4.X | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Soap UI | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Junit | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Maven | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Jboss | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Eclipse Neon | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
SonarQube | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
SVN /GitHub | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Database Infrastructure Requirements | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Data Model creation | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Database Design | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Database Design Review | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
DDL & DML Creation | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
DDL & DML Review | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Infrastructure - Setup - UAT | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
UI - UX Development Requirements | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Visual Studio Code | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Node.js | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Angular 6, Karma & Jasmin | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
SVN /GitHub | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Bootstrap | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Integration Development | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Common Services Development Requirements | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Postman | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
SOAP UI | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Integration Development Requirements | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Java 1.8 | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Spring 5.x | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Hibernate 4.X | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Soap UI | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Junit | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Maven | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Jboss | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Eclipse Neon | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
SonarQube | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
SVN /GitHub | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Database Infrastructure Requirements | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Data Model creation | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Database Design | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Database Design Review | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
DDL & DML Creation | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
DDL & DML Review | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Infrastructure - Setup - Prod | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
UI - UX Development Requirements | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Visual Studio Code | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Node.js | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Angular 6, Karma & Jasmin | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
SVN /GitHub | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Bootstrap | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Integration Development | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Common Services Development Requirements | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Postman | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
SOAP UI | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Integration Development Requirements | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Java 1.8 | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Spring 5.x | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Hibernate 4.X | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Soap UI | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Junit | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Maven | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Jboss | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Eclipse Neon | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
SonarQube | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
SVN /GitHub | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Database Infrastructure Requirements | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Data Model creation | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Database Design | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
Database Design Review | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
DDL & DML Creation | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
DDL & DML Review | 51d | Fri 2/8/19 | Fri 4/19/19 |  | HRSS - APS | krangard/KJ Davis | V. Build
BUILD & TEST | 51d | Thu 3/7/19 | Thu 5/16/19
Build | 30d | Thu 3/7/19 | Wed 4/17/19 | 74,66
Configure & Build Solution | 30d | Thu 3/7/19 | Wed 4/17/19
Show & Tell - Demonstration of Functionality for Validation by Amazon | 1d | Thu 3/7/19 | Thu 3/7/19 |  | Digital PM/Project PM | Mohan/Ken | V. Build
LTI will perform a walk-thorugh of new functionality as completed in Development | 1d | Thu 3/7/19 | Thu 3/7/19 |  | Digital PM/Project PM | Mohan/Ken | V. Build
Reviews to be scheduled as functionality becomes avaialble | 1d | Thu 3/7/19 | Thu 3/7/19 |  | Digital PM/Project PM | Mohan/Ken | V. Build
Redirect to Self Service Portal (SMF 1.0) | 30d | Thu 3/7/19 | Wed 4/17/19 |  | Digital PM/Project PM | Mohan/Ken | V. Build
SMF - Pick Transaction - User and Transaction Rules - Redirect PP | 15d | Thu 3/7/19 | Wed 3/27/19 |  | Digital PM/Project PM | Mohan/Ken | V. Build
Personal Details - Self Service | 30d | Thu 3/7/19 | Wed 4/17/19 |  | Business Analyst | Varun/Mohan | V. Build
Address - Contact Details - Disability - Emergency Contact - Ethnicity - Gender - Preferred Name - Vetran info | 15d | Thu 3/7/19 | Wed 3/27/19 |  | Business Analyst | Varun/Mohan | V. Build
Sprint 1 - Address - Contact Details - Emergency Contact | 15d | Thu 3/7/19 | Wed 3/27/19
UI - UX Development | 15d | Thu 3/7/19 | Wed 3/27/19 |  | UX/UI Leads | Koteswararao/Sugur | V. Build
Common Services Development (SSO, Fetch Data from External Systems) | 15d | Thu 3/7/19 | Wed 3/27/19 |  | Integration Lead | Mayuresh/Santosh | V. Build
Integration Development | 15d | Thu 3/7/19 | Wed 3/27/19 |  | Integration Lead | Mayuresh/Santosh | V. Build
Database Development | 15d | Thu 3/7/19 | Wed 3/27/19 |  | DBA | DBA | V. Build
Amazon Iterative Review | 15d | Thu 3/7/19 | Wed 3/27/19
Amazon Sign Off | 1d | Wed 3/27/19 | Wed 3/27/19
Sprint 2 - Ethinicity - Gender - Preferred Name | 15d | Thu 3/28/19 | Wed 4/17/19 | 205
UI - UX Development by User Stories | 15d | Thu 3/28/19 | Wed 4/17/19 |  | UX/UI Leads | Koteswararao/Sugur | V. Build
Common Services Development (SSO, Fetch Data from External Systems) | 15d | Thu 3/28/19 | Wed 4/17/19 |  | Integration Lead | Mayuresh/Santosh | V. Build
Integration Development | 15d | Thu 3/28/19 | Wed 4/17/19 |  | Integration Lead | Mayuresh/Santosh | V. Build
Database Development | 15d | Thu 3/28/19 | Wed 4/17/19 |  | DBA | DBA | V. Build
Amazon Iterative Review | 15d | Thu 3/28/19 | Wed 4/17/19
Amazon Sign Off | 1d | Wed 4/17/19 | Wed 4/17/19
Job Data - Self Service | 30d | Thu 3/7/19 | Wed 4/17/19 |  | Business Analyst | Varun/Mohan | V. Build
Business Title - Company - Department - FCLM Area and FCLM job - Full Time - Part Time - Pay Group - Product Line - Shift Pattern and ADP shift - Supervisor Change - Transfer | 15d | Thu 3/7/19 | Wed 3/27/19 |  | Business Analyst | Varun/Mohan | V. Build
Sprint 1 - Business Title - Company - Department - FCLM Area and FCLM job - Full Time - Part Time - Pay Group - | 15d | Thu 3/7/19 | Wed 3/27/19 | 66
UI - UX Development by User Stories | 15d | Thu 3/7/19 | Wed 3/27/19 |  | UX/UI Leads | Koteswararao/Sugur | V. Build
Common Services Development (SSO, Fetch Data from External Systems) | 15d | Thu 3/7/19 | Wed 3/27/19 |  | Integration Lead | Mayuresh/Santosh | V. Build
Integration Development | 15d | Thu 3/7/19 | Wed 3/27/19 |  | Integration Lead | Mayuresh/Santosh | V. Build
Database Development | 15d | Thu 3/7/19 | Wed 3/27/19 |  | DBA | DBA | V. Build
Amazon Iterative Review | 15d | Thu 3/7/19 | Wed 3/27/19
Amazon Sign Off | 1d | Wed 3/27/19 | Wed 3/27/19
Sprint 2 - Product Line - Shift Pattern and ADP shift - Supervisor Change - Transfer | 15d | Thu 3/28/19 | Wed 4/17/19 | 295338
UI/UX Development by User Stories | 15d | Thu 3/28/19 | Wed 4/17/19 |  | UX/UI Leads | Koteswararao/Sugur | V. Build
Common Services Development (SSO, Fetch Data from External Systems) | 15d | Thu 3/28/19 | Wed 4/17/19 |  | Integration Lead | Mayuresh/Santosh | V. Build
Integration Development | 15d | Thu 3/28/19 | Wed 4/17/19 | 66 | Integration Lead | Mayuresh/Santosh | V. Build
Database Development | 15d | Thu 3/28/19 | Wed 4/17/19 |  | DBA | DBA | V. Build
Amazon Iterative Review | 15d | Thu 3/28/19 | Wed 4/17/19
No Self Service (SMF 1.1) - Structured Input & Ticket Creation | 30d | Thu 3/7/19 | Wed 4/17/19 |  | Business Analyst | Varun/Mohan | V. Build
SMF - Pick Transaction - User and Transaction Rules - Create Ticket | 15d | Thu 3/7/19 | Wed 3/27/19 |  | Business Analyst | Varun/Mohan | V. Build
Personal Details | 30d | Thu 3/7/19 | Wed 4/17/19 |  | Business Analyst | Varun/Mohan | V. Build
Individual Only | 30d | Thu 3/7/19 | Wed 4/17/19 |  | Business Analyst | Varun/Mohan | V. Build
Individual request is a request which is made for a single person. It can be made by a manager, HRBP or any other type of employee (example recruiter) for self and for other. | 15d | Thu 3/7/19 | Wed 3/27/19
Legal Name - SSN - SIN - National ID - CRI National ID | 15d | Thu 3/7/19 | Wed 3/27/19 |  | Business Analyst | Varun/Mohan | V. Build
Sprint 1 - Legal Name - SSN - SIN | 15d | Thu 3/7/19 | Wed 3/27/19
UI - UX Development by User Stories | 15d | Thu 3/7/19 | Wed 3/27/19 |  | UX/UI Leads | Koteswararao/Sugur | V. Build
Page Design - HTML | 3d | Thu 3/7/19 | Mon 3/11/19 |  | UX/UI Leads | Koteswararao/Sugur | V. Build
Responsive Design | 3d | Tue 3/12/19 | Thu 3/14/19 | 390 | UX/UI Leads | Koteswararao/Sugur | V. Build
Browser Compatibility | 3d | Tue 3/12/19 | Thu 3/14/19 | 390 | UX/UI Leads | Koteswararao/Sugur | V. Build
Routing | 3d | Tue 3/12/19 | Thu 3/14/19 | 390 | UX/UI Leads | Koteswararao/Sugur | V. Build
Component / Service/ Model Creation | 5d | Tue 3/12/19 | Mon 3/18/19 | 390 | UX/UI Leads | Koteswararao/Sugur | V. Build
Validation | 2d | Tue 3/19/19 | Wed 3/20/19 | 394 | UX/UI Leads | Koteswararao/Sugur | V. Build
Prepare Service Contract (JSON) | 1d | Tue 3/12/19 | Tue 3/12/19 | 390 | UX/UI Leads | Koteswararao/Sugur | V. Build
Code review - Peer / Lead | 5d | Thu 3/21/19 | Wed 3/27/19 | 395 | UX/UI Leads | Koteswararao/Sugur | V. Build
Common Services Development (SSO, Fetch Data from External Systems) | 15d | Thu 3/7/19 | Wed 3/27/19 |  | Integration Lead | Mayuresh/Santosh | V. Build
Contract Creation (JSON) | 2d | Thu 3/7/19 | Fri 3/8/19 | 66 | Integration Lead | Mayuresh/Santosh | V. Build
Entity Creation | 2d | Thu 3/7/19 | Fri 3/8/19 | 66 | Integration Lead | Mayuresh/Santosh | V. Build
Logging | 2d | Thu 3/7/19 | Fri 3/8/19 | 66 | Integration Lead | Mayuresh/Santosh | V. Build
Exception / Error Handling | 2d | Thu 3/7/19 | Fri 3/8/19 | 66 | Integration Lead | Mayuresh/Santosh | V. Build
Module creation | 1d | Thu 3/7/19 | Thu 3/7/19 | 66 | Integration Lead | Mayuresh/Santosh | V. Build
Controller Creation | 2d | Fri 3/8/19 | Mon 3/11/19 | 403 | Integration Lead | Mayuresh/Santosh | V. Build
Service Creation | 1d | Thu 3/21/19 | Thu 3/21/19 | 395 | Integration Lead | Mayuresh/Santosh | V. Build
Transformation / Business rules | 2d | Fri 3/22/19 | Mon 3/25/19 | 405 | Integration Lead | Mayuresh/Santosh | V. Build
Configuration / Property file creation | 1d | Tue 3/26/19 | Tue 3/26/19 | 406 | Integration Lead | Mayuresh/Santosh | V. Build
Utility creation | 2d | Tue 3/26/19 | Wed 3/27/19 | 406 | Integration Lead | Mayuresh/Santosh | V. Build
Constant File | 1d | Tue 3/26/19 | Tue 3/26/19 | 406 | Integration Lead | Mayuresh/Santosh | V. Build
Code Review - Peer / Lead | 1d | Tue 3/26/19 | Tue 3/26/19 | 406 | Integration Lead | Mayuresh/Santosh | V. Build
Integration Development | 15d | Thu 3/7/19 | Wed 3/27/19 | 66 | Integration Lead | Mayuresh/Santosh | V. Build
Contract Creation (JSON) | 2d | Thu 3/7/19 | Fri 3/8/19 |  | Integration Lead | Mayuresh/Santosh | V. Build
Entity Creation | 2d | Thu 3/7/19 | Fri 3/8/19 |  | Integration Lead | Mayuresh/Santosh | V. Build
Logging | 2d | Mon 3/11/19 | Tue 3/12/19 | 413 | Integration Lead | Mayuresh/Santosh | V. Build
Exception / Error Handling | 2d | Wed 3/13/19 | Thu 3/14/19 | 414 | Integration Lead | Mayuresh/Santosh | V. Build
Module creation | 2d | Fri 3/15/19 | Mon 3/18/19 | 415 | Integration Lead | Mayuresh/Santosh | V. Build
Controller Creation | 2d | Tue 3/19/19 | Wed 3/20/19 | 416 | Integration Lead | Mayuresh/Santosh | V. Build
Service Creation | 3d | Thu 3/21/19 | Mon 3/25/19 | 417 | Integration Lead | Mayuresh/Santosh | V. Build
Transformation / Business rules | 2d | Tue 3/26/19 | Wed 3/27/19 | 418 | Integration Lead | Mayuresh/Santosh | V. Build
Configuration / Property file creation | 2d | Tue 3/26/19 | Wed 3/27/19 | 418 | Integration Lead | Mayuresh/Santosh | V. Build
Utility creation | 2d | Tue 3/26/19 | Wed 3/27/19 | 418 | Integration Lead | Mayuresh/Santosh | V. Build
Constant File | 2d | Tue 3/26/19 | Wed 3/27/19 | 418 | Integration Lead | Mayuresh/Santosh | V. Build
Code Review - Peer / Lead | 2d | Tue 3/26/19 | Wed 3/27/19 | 418 | Integration Lead | Mayuresh/Santosh | V. Build
Database Development | 15d | Thu 3/7/19 | Wed 3/27/19 |  | DBA | DBA | V. Build
Data Model creation | 15d | Thu 3/7/19 | Wed 3/27/19 |  | DBA | DBA | V. Build
Database Design | 15d | Thu 3/7/19 | Wed 3/27/19 |  | DBA | DBA | V. Build
Database Design Review | 15d | Thu 3/7/19 | Wed 3/27/19 |  | DBA | DBA | V. Build
DDL & DML Creation | 15d | Thu 3/7/19 | Wed 3/27/19 |  | DBA | DBA | V. Build
DDL & DML Review | 15d | Thu 3/7/19 | Wed 3/27/19 |  | DBA | DBA | V. Build
Amazon Iterative Review | 15d | Thu 3/7/19 | Wed 3/27/19
Amazon Sign Off | 1d | Wed 3/27/19 | Wed 3/27/19
Sprint 2 - National ID - CRI National ID | 15d | Thu 3/28/19 | Wed 4/17/19 | 388
Individual or Bulk | 30d | Thu 3/7/19 | Wed 4/17/19 |  | Business Analyst | Varun/Mohan | V. Build
When a request is made for more than 1 person it is treated as mass update request, traditionally these request often come in excel files of different format. | 15d | Thu 3/7/19 | Wed 3/27/19
Gender/Deemed Export Info/National Insurance Number/Date of Birth/Visual Survey Conducted/Bank Account Number/Bank Account details/Marital Status | 15d | Thu 3/7/19 | Wed 3/27/19 |  | Business Analyst | Varun/Mohan | V. Build
Sprint 1 - Gender/Deemed Export Info/National Insurance Number/Date of Birth/Visual Survey Conducted | 15d | Thu 3/7/19 | Wed 3/27/19 | 66
UI - UX Development by User Stories | 15d | Thu 3/7/19 | Wed 3/27/19 |  | UX/UI Leads | Koteswararao/Sugur | V. Build
Page Design - HTML | 3d | Thu 3/7/19 | Mon 3/11/19 |  | UX/UI Leads | Koteswararao/Sugur | V. Build
Responsive Design | 3d | Tue 3/12/19 | Thu 3/14/19 | 483 | UX/UI Leads | Koteswararao/Sugur | V. Build
Browser Compatibility | 3d | Tue 3/12/19 | Thu 3/14/19 | 483 | UX/UI Leads | Koteswararao/Sugur | V. Build
Routing | 3d | Tue 3/12/19 | Thu 3/14/19 | 483 | UX/UI Leads | Koteswararao/Sugur | V. Build
Component / Service/ Model Creation | 5d | Tue 3/12/19 | Mon 3/18/19 | 483 | UX/UI Leads | Koteswararao/Sugur | V. Build
Validation | 2d | Tue 3/19/19 | Wed 3/20/19 | 487 | UX/UI Leads | Koteswararao/Sugur | V. Build
Prepare Service Contract (JSON) | 1d | Tue 3/12/19 | Tue 3/12/19 | 483 | UX/UI Leads | Koteswararao/Sugur | V. Build
Code review - Peer / Lead | 5d | Thu 3/21/19 | Wed 3/27/19 | 488 | UX/UI Leads | Koteswararao/Sugur | V. Build
Common Services Development (SSO, Fetch Data from External Systems) | 15d | Thu 3/7/19 | Wed 3/27/19 |  | Integration Lead | Mayuresh/Santosh | V. Build
Contract Creation (JSON) | 2d | Thu 3/7/19 | Fri 3/8/19 |  | Integration Lead | Mayuresh/Santosh | V. Build
Entity Creation | 2d | Thu 3/7/19 | Fri 3/8/19 |  | Integration Lead | Mayuresh/Santosh | V. Build
Logging | 2d | Thu 3/7/19 | Fri 3/8/19 |  | Integration Lead | Mayuresh/Santosh | V. Build
Exception / Error Handling | 2d | Thu 3/7/19 | Fri 3/8/19 |  | Integration Lead | Mayuresh/Santosh | V. Build
Module creation | 1d | Thu 3/7/19 | Thu 3/7/19 |  | Integration Lead | Mayuresh/Santosh | V. Build
Controller Creation | 2d | Fri 3/8/19 | Mon 3/11/19 | 496 | Integration Lead | Mayuresh/Santosh | V. Build
Service Creation | 1d | Thu 3/21/19 | Thu 3/21/19 | 488 | Integration Lead | Mayuresh/Santosh | V. Build
Transformation / Business rules | 2d | Fri 3/22/19 | Mon 3/25/19 | 498 | Integration Lead | Mayuresh/Santosh | V. Build
Configuration / Property file creation | 1d | Tue 3/26/19 | Tue 3/26/19 | 499 | Integration Lead | Mayuresh/Santosh | V. Build
Utility creation | 2d | Tue 3/26/19 | Wed 3/27/19 | 499 | Integration Lead | Mayuresh/Santosh | V. Build
Constant File | 1d | Tue 3/26/19 | Tue 3/26/19 | 499 | Integration Lead | Mayuresh/Santosh | V. Build
Code Review - Peer / Lead | 1d | Tue 3/26/19 | Tue 3/26/19 | 499 | Integration Lead | Mayuresh/Santosh | V. Build
Integration Development | 15d | Thu 3/7/19 | Wed 3/27/19 |  | Integration Lead | Mayuresh/Santosh | V. Build
Contract Creation (JSON) | 2d | Thu 3/7/19 | Fri 3/8/19 |  | Integration Lead | Mayuresh/Santosh | V. Build
Entity Creation | 2d | Thu 3/7/19 | Fri 3/8/19 |  | Integration Lead | Mayuresh/Santosh | V. Build
Logging | 2d | Mon 3/11/19 | Tue 3/12/19 | 506 | Integration Lead | Mayuresh/Santosh | V. Build
Exception / Error Handling | 2d | Wed 3/13/19 | Thu 3/14/19 | 507 | Integration Lead | Mayuresh/Santosh | V. Build
Module creation | 2d | Fri 3/15/19 | Mon 3/18/19 | 508 | Integration Lead | Mayuresh/Santosh | V. Build
Controller Creation | 2d | Tue 3/19/19 | Wed 3/20/19 | 509 | Integration Lead | Mayuresh/Santosh | V. Build
Service Creation | 3d | Thu 3/21/19 | Mon 3/25/19 | 510 | Integration Lead | Mayuresh/Santosh | V. Build
Transformation / Business rules | 2d | Tue 3/26/19 | Wed 3/27/19 | 511 | Integration Lead | Mayuresh/Santosh | V. Build
Configuration / Property file creation | 2d | Tue 3/26/19 | Wed 3/27/19 | 511 | Integration Lead | Mayuresh/Santosh | V. Build
Utility creation | 2d | Tue 3/26/19 | Wed 3/27/19 | 511 | Integration Lead | Mayuresh/Santosh | V. Build
Constant File | 2d | Tue 3/26/19 | Wed 3/27/19 | 511 | Integration Lead | Mayuresh/Santosh | V. Build
Code Review - Peer / Lead | 2d | Tue 3/26/19 | Wed 3/27/19 | 511 | Integration Lead | Mayuresh/Santosh | V. Build
Database Development | 15d | Thu 3/7/19 | Wed 3/27/19 |  | DBA | DBA | V. Build
Data Model creation | 15d | Thu 3/7/19 | Wed 3/27/19 |  | DBA | DBA | V. Build
Database Design | 15d | Thu 3/7/19 | Wed 3/27/19 |  | DBA | DBA | V. Build
Database Design Review | 15d | Thu 3/7/19 | Wed 3/27/19 |  | DBA | DBA | V. Build
DDL & DML Creation | 15d | Thu 3/7/19 | Wed 3/27/19 |  | DBA | DBA | V. Build
DDL & DML Review | 15d | Thu 3/7/19 | Wed 3/27/19 |  | DBA | DBA | V. Build
Amazon Iterative Review | 15d | Thu 3/7/19 | Wed 3/27/19
Amazon Sign Off | 1d | Wed 3/27/19 | Wed 3/27/19
Sprint 2 - Bank Account Number/Bank Account details/Marital Status | 15d | Thu 3/28/19 | Wed 4/17/19 | 481
UI/UX Development by User Stories | 15d | Thu 3/28/19 | Wed 4/17/19 |  | UX/UI Leads | Koteswararao/Sugur | V. Build
Page Design - HTML | 3d | Thu 3/28/19 | Mon 4/1/19 |  | UX/UI Leads | Koteswararao/Sugur | V. Build
Responsive Design | 3d | Tue 4/2/19 | Thu 4/4/19 | 527 | UX/UI Leads | Koteswararao/Sugur | V. Build
Browser Compatibility | 3d | Tue 4/2/19 | Thu 4/4/19 | 527 | UX/UI Leads | Koteswararao/Sugur | V. Build
Routing | 3d | Tue 4/2/19 | Thu 4/4/19 | 527 | UX/UI Leads | Koteswararao/Sugur | V. Build
Component / Service/ Model Creation | 5d | Tue 4/2/19 | Mon 4/8/19 | 527 | UX/UI Leads | Koteswararao/Sugur | V. Build
Validation | 2d | Tue 4/9/19 | Wed 4/10/19 | 531 | UX/UI Leads | Koteswararao/Sugur | V. Build
Prepare Service Contract (JSON) | 1d | Tue 4/2/19 | Tue 4/2/19 | 527 | UX/UI Leads | Koteswararao/Sugur | V. Build
Code review - Peer / Lead | 5d | Thu 4/11/19 | Wed 4/17/19 | 532 | UX/UI Leads | Koteswararao/Sugur | V. Build
Common Services Development (SSO, Fetch Data from External Systems) | 15d | Thu 3/28/19 | Wed 4/17/19 |  | Integration Lead | Mayuresh/Santosh | V. Build
Contract Creation (JSON) | 2d | Thu 3/28/19 | Fri 3/29/19 | 66 | Integration Lead | Mayuresh/Santosh | V. Build
Entity Creation | 2d | Thu 3/28/19 | Fri 3/29/19 | 66 | Integration Lead | Mayuresh/Santosh | V. Build
Logging | 2d | Thu 3/28/19 | Fri 3/29/19 | 66 | Integration Lead | Mayuresh/Santosh | V. Build
Exception / Error Handling | 2d | Thu 3/28/19 | Fri 3/29/19 | 66 | Integration Lead | Mayuresh/Santosh | V. Build
Module creation | 1d | Thu 3/28/19 | Thu 3/28/19 | 66 | Integration Lead | Mayuresh/Santosh | V. Build
Controller Creation | 2d | Fri 3/29/19 | Mon 4/1/19 | 540 | Integration Lead | Mayuresh/Santosh | V. Build
Service Creation | 1d | Thu 4/11/19 | Thu 4/11/19 | 532 | Integration Lead | Mayuresh/Santosh | V. Build
Transformation / Business rules | 2d | Fri 4/12/19 | Mon 4/15/19 | 542 | Integration Lead | Mayuresh/Santosh | V. Build
Configuration / Property file creation | 1d | Tue 4/16/19 | Tue 4/16/19 | 543 | Integration Lead | Mayuresh/Santosh | V. Build
Utility creation | 2d | Tue 4/16/19 | Wed 4/17/19 | 543 | Integration Lead | Mayuresh/Santosh | V. Build
Constant File | 1d | Tue 4/16/19 | Tue 4/16/19 | 543 | Integration Lead | Mayuresh/Santosh | V. Build
Code Review - Peer / Lead | 1d | Tue 4/16/19 | Tue 4/16/19 | 543 | Integration Lead | Mayuresh/Santosh | V. Build
Integration Development | 15d | Thu 3/28/19 | Wed 4/17/19 |  | Integration Lead | Mayuresh/Santosh | V. Build
Contract Creation (JSON) | 2d | Thu 3/28/19 | Fri 3/29/19 |  | Integration Lead | Mayuresh/Santosh | V. Build
Entity Creation | 2d | Thu 3/28/19 | Fri 3/29/19 |  | Integration Lead | Mayuresh/Santosh | V. Build
Logging | 2d | Mon 4/1/19 | Tue 4/2/19 | 550 | Integration Lead | Mayuresh/Santosh | V. Build
Exception / Error Handling | 2d | Wed 4/3/19 | Thu 4/4/19 | 551 | Integration Lead | Mayuresh/Santosh | V. Build
Module creation | 2d | Fri 4/5/19 | Mon 4/8/19 | 552 | Integration Lead | Mayuresh/Santosh | V. Build
Controller Creation | 2d | Tue 4/9/19 | Wed 4/10/19 | 553 | Integration Lead | Mayuresh/Santosh | V. Build
Service Creation | 3d | Thu 4/11/19 | Mon 4/15/19 | 554 | Integration Lead | Mayuresh/Santosh | V. Build
Transformation / Business rules | 2d | Tue 4/16/19 | Wed 4/17/19 | 555 | Integration Lead | Mayuresh/Santosh | V. Build
Configuration / Property file creation | 2d | Tue 4/16/19 | Wed 4/17/19 | 555 | Integration Lead | Mayuresh/Santosh | V. Build
Utility creation | 2d | Tue 4/16/19 | Wed 4/17/19 | 555 | Integration Lead | Mayuresh/Santosh | V. Build
Constant File | 2d | Tue 4/16/19 | Wed 4/17/19 | 555 | Integration Lead | Mayuresh/Santosh | V. Build
Code Review - Peer / Lead | 2d | Tue 4/16/19 | Wed 4/17/19 | 555 | Integration Lead | Mayuresh/Santosh | V. Build
Database Development | 15d | Thu 3/28/19 | Wed 4/17/19 |  | DBA | DBA | V. Build
Data Model creation | 15d | Thu 3/28/19 | Wed 4/17/19 |  | DBA | DBA | V. Build
Database Design | 15d | Thu 3/28/19 | Wed 4/17/19 |  | DBA | DBA | V. Build
Database Design Review | 15d | Thu 3/28/19 | Wed 4/17/19 |  | DBA | DBA | V. Build
DDL & DML Creation | 15d | Thu 3/28/19 | Wed 4/17/19 |  | DBA | DBA | V. Build
DDL & DML Review | 15d | Thu 3/28/19 | Wed 4/17/19 |  | DBA | DBA | V. Build
Amazon Iterative Review | 15d | Thu 3/28/19 | Wed 4/17/19
Amazon Sign Off | 1d | Wed 4/17/19 | Wed 4/17/19
Job Data | 30d | Thu 3/7/19 | Wed 4/17/19 |  | Business Analyst | Varun/Mohan | V. Build
Individual Only | 30d | Thu 3/7/19 | Wed 4/17/19 |  | Business Analyst | Varun/Mohan | V. Build
Individual request is a request which is made for a single person. It can be made by a manager, HRBP or any other type of employee (example recruiter) for self and for other. | 15d | Thu 3/7/19 | Wed 3/27/19
Amazon Discount Code - Business Unit Change - CORP Addendum - EA Changes - Eligibility - Ops Addendum - Part time Work Arrangement- FWA - Public Transportation Reimbursement - Suspension - Telecommuting-Individual | 15d | Thu 3/7/19 | Wed 3/27/19 |  | Business Analyst | Varun/Mohan | V. Build
Sprint 1 - Amazon Discount Code - Business Unit Change - CORP Addendum - EA Changes - Eligibility - Ops Addendum | 15d | Thu 3/7/19 | Wed 3/27/19
UI - UX Development by User Stories | 15d | Thu 3/7/19 | Wed 3/27/19 |  | UX/UI Leads | Koteswararao/Sugur | V. Build
Common Services Development (SSO, Fetch Data from External Systems) | 15d | Thu 3/7/19 | Wed 3/27/19 |  | Integration Lead | Mayuresh/Santosh | V. Build
Integration Development | 15d | Thu 3/7/19 | Wed 3/27/19 |  | Integration Lead | Mayuresh/Santosh | V. Build
Database Development | 15d | Thu 3/7/19 | Wed 3/27/19 |  | DBA | DBA | V. Build
Amazon Iterative Review | 15d | Thu 3/7/19 | Wed 3/27/19
Amazon Sign Off | 1d | Wed 3/27/19 | Wed 3/27/19
Sprint 2 - Change - CORP Addendum - EA Changes - Eligibility - Ops Addendum - Part time Work Arrangement- FWA - Public Transportation Reimbursement - Suspension - Telecommuting-Individual | 15d | Thu 3/28/19 | Wed 4/17/19 | 573
UI/UX Development by User Stories | 15d | Thu 3/28/19 | Wed 4/17/19 |  | UX/UI Leads | Koteswararao/Sugur | V. Build
Common Services Development (SSO, Fetch Data from External Systems) | 15d | Thu 3/28/19 | Wed 4/17/19 |  | Integration Lead | Mayuresh/Santosh | V. Build
Integration Development | 15d | Thu 3/28/19 | Wed 4/17/19 |  | Integration Lead | Mayuresh/Santosh | V. Build
Database Development | 15d | Thu 3/28/19 | Wed 4/17/19 |  | DBA | DBA | V. Build
Amazon Iterative Review | 15d | Thu 3/28/19 | Wed 4/17/19
Amazon Sign Off | 1d | Wed 4/17/19 | Wed 4/17/19
Individual or Bulk | 30d | Thu 3/7/19 | Wed 4/17/19 |  | Business Analyst | Varun/Mohan | V. Build
When a request is made for more than 1 person it is treated as mass update request, traditionally these request often come in excel files of different format. | 0d | Thu 3/7/19 | Thu 3/7/19
Additional Pay(Suppliment bonus, cash bonus and sales incentive,SignOn Bounus ) - Agency - Company - Compensation - Employment Date - Job Code - Location | 0d | Thu 3/7/19 | Thu 3/7/19 |  | Business Analyst | Varun/Mohan | V. Build
M&A Hire - Re-Hire - Paygroup - Payrate - Product Line - Promotions - Seasonal-Individual - Shift- Individual(CR) | 0d | Thu 3/7/19 | Thu 3/7/19 |  | Business Analyst | Varun/Mohan | V. Build
Standard Hours/Status Change/Suspension | 0d | Thu 3/7/19 | Thu 3/7/19 |  | Business Analyst | Varun/Mohan | V. Build
Sprint 1 - Additional Pay(Suppliment bonus, cash bonus and sales incentive,SignOn Bounus ) - Agency - Company - Compensation - Employment Date - Job Code - Location | 15d | Thu 3/7/19 | Wed 3/27/19
UI - UX Development by User Stories | 15d | Thu 3/7/19 | Wed 3/27/19 |  | UX/UI Leads | Koteswararao/Sugur | V. Build
Common Services Development (SSO, Fetch Data from External Systems) | 15d | Thu 3/7/19 | Wed 3/27/19 |  | Integration Lead | Mayuresh/Santosh | V. Build
Integration Development | 15d | Thu 3/7/19 | Wed 3/27/19 |  | Integration Lead | Mayuresh/Santosh | V. Build
Database Development | 15d | Thu 3/7/19 | Wed 3/27/19 |  | DBA | DBA | V. Build
Amazon Iterative Review | 15d | Thu 3/7/19 | Wed 3/27/19
Amazon Sign Off | 1d | Wed 3/27/19 | Wed 3/27/19
Sprint 2 - Additional Pay(Suppliment bonus, cash bonus and sales incentive,SignOn Bounus ) - Agency - Company - Compensation - Employment Date - Job Code - Location | 15d | Thu 3/28/19 | Wed 4/17/19 | 709708
UI/UX Development by User Stories | 15d | Thu 3/28/19 | Wed 4/17/19 |  | UX/UI Leads | Koteswararao/Sugur | V. Build
Common Services Development (SSO, Fetch Data from External Systems) | 15d | Thu 3/28/19 | Wed 4/17/19 |  | Integration Lead | Mayuresh/Santosh | V. Build
Integration Development | 15d | Thu 3/28/19 | Wed 4/17/19 |  | Integration Lead | Mayuresh/Santosh | V. Build
Database Development | 15d | Thu 3/28/19 | Wed 4/17/19 |  | DBA | DBA | V. Build
Amazon Iterative Review | 15d | Thu 3/28/19 | Wed 4/17/19
Amazon Sign Off | 1d | Wed 4/17/19 | Wed 4/17/19
Configurable Screens and Exceptions | 30d | Thu 3/7/19 | Wed 4/17/19 | 48 | Business Analyst | Varun/Mohan | V. Build
Configurable Screen for Self Service URLs | 15d | Thu 3/7/19 | Wed 3/27/19
Ability for an Administrator to remove, add, or update Self Service URLs in Smartform | 15d | Thu 3/7/19 | Wed 3/27/19 |  | Development Leads | Siva/Mayuresh/Koteswararao | V. Build
Sprint 1 - Configurable Screen for Self Service | 15d | Thu 3/7/19 | Wed 3/27/19
UI/UX Development | 15d | Thu 3/7/19 | Wed 3/27/19 |  | UX/UI Leads | Koteswararao/Sugur | V. Build
Common Services Development (SSO, Fetch Data from External Systems) | 15d | Thu 3/7/19 | Wed 3/27/19 |  | Integration Lead | Mayuresh/Santosh | V. Build
Integration Development | 15d | Thu 3/7/19 | Wed 3/27/19 |  | Integration Lead | Mayuresh/Santosh | V. Build
Database Development | 15d | Thu 3/7/19 | Wed 3/27/19 |  | DBA | DBA | V. Build
Amazon Iterative Review | 15d | Thu 3/7/19 | Wed 3/27/19
Amazon Sign Off | 1d | Wed 3/27/19 | Wed 3/27/19
Escape Valve | 15d | Thu 3/28/19 | Wed 4/17/19 | 757 | Business Analyst | Varun/Mohan | V. Build
At any time there would be Escape Valve depending on request for the requester inside a smart form. Which could generate a ticket out using quick link or WFA API depending upon type of request. | 15d | Thu 3/28/19 | Wed 4/17/19 |  | Business Analyst | Varun/Mohan | V. Build
Escape Valve should capture the reason within smart form on why the requester need to generate a ticket before generating the ticket. Reason can be stored and easily reportable if need to be | 15d | Thu 3/28/19 | Wed 4/17/19 |  | Business Analyst | Varun/Mohan | V. Build
My request does not fall in any category - Request is for someone who is not active employee - Portal is not supporting my attachment for mass update | 15d | Thu 3/28/19 | Wed 4/17/19 |  | Business Analyst | Varun/Mohan | V. Build
Sprint 2 - Configurable Screen for Self Service Escape - Valve | 15d | Thu 3/28/19 | Wed 4/17/19 | 757
UI/UX Development | 15d | Thu 3/28/19 | Wed 4/17/19 |  | UX/UI Leads | Koteswararao/Sugur | V. Build
Common Services Development (SSO, Fetch Data from External Systems) | 15d | Thu 3/28/19 | Wed 4/17/19 |  | Integration Lead | Mayuresh/Santosh | V. Build
Integration Development | 15d | Thu 3/28/19 | Wed 4/17/19 |  | Integration Lead | Mayuresh/Santosh | V. Build
Database Development | 15d | Thu 3/28/19 | Wed 4/17/19 |  | DBA | DBA | V. Build
Amazon Iterative Review | 15d | Thu 3/28/19 | Wed 4/17/19
Amazon Sign Off | 1d | Wed 4/17/19 | Wed 4/17/19
Test Planning & Execution | 10d | Thu 3/7/19 | Wed 3/20/19
Test Planning | 10d | Thu 3/7/19 | Wed 3/20/19 | 66
Redirect to Self Service Portal (SMF 1.0) | 10d | Thu 3/7/19 | Wed 3/20/19 |  | Digital PM/Project PM | Mohan/Ken | VI. Test
SMF - Pick Transaction - User and Transaction Rules - Redirect PP | 10d | Thu 3/7/19 | Wed 3/20/19 |  |  |  | VI. Test
Test Planning Project Artifacts | 10d | Thu 3/7/19 | Wed 3/20/19 |  | Business Analyst | Varun/Mohan | VI. Test
Amazon Iterative Review | 10d | Thu 3/7/19 | Wed 3/20/19
Amazon Sign Off | 1d | Wed 3/20/19 | Wed 3/20/19
No Self Service (SMF 1.1) - Structured Input & Ticket Creation | 10d | Thu 3/7/19 | Wed 3/20/19 |  | Business Analyst | Varun/Mohan | VI. Test
SMF - Pick Transaction - User and Transaction Rules - Create Ticket | 10d | Thu 3/7/19 | Wed 3/20/19 |  | Business Analyst | Varun/Mohan | VI. Test
Test Planning Project Artifacts | 10d | Thu 3/7/19 | Wed 3/20/19 |  | QA Lead / UAT Lead | LTI / Ahbi/Anand | VI. Test
Amazon Iterative Review | 10d | Thu 3/7/19 | Wed 3/20/19
Amazon Sign Off | 1d | Wed 3/20/19 | Wed 3/20/19
Configurable Screens and Exceptions | 10d | Thu 3/7/19 | Wed 3/20/19 |  | Business Analyst | Varun/Mohan | VI. Test
Configurable Screen for Self Service URLs | 10d | Thu 3/7/19 | Wed 3/20/19 |  | Development Leads | Siva/Mayuresh/Koteswararao | VI. Test
Escape Valve | 0d | Thu 3/7/19 | Thu 3/7/19 |  | Business Analyst | Varun/Mohan | VI. Test
Test Planning Project Artifacts | 10d | Thu 3/7/19 | Wed 3/20/19 |  | Business Analyst | Varun/Mohan | VI. Test
Amazon Iterative Review | 10d | Thu 3/7/19 | Wed 3/20/19
Amazon Sign Off | 1d | Wed 3/20/19 | Wed 3/20/19
Testing | 10d | Thu 4/18/19 | Wed 5/1/19 | 848847800799
Sytstem Integration Testing | 5d | Thu 4/18/19 | Wed 4/24/19 |  | Test Lead | Rajesh Bachala | VI. Test
Redirect to Self Service Portal (SMF 1.0) | 5d | Thu 4/18/19 | Wed 4/24/19 |  | Digital PM/Project PM | Mohan/Ken | VI. Test
SMF - Pick Transaction - User and Transaction Rules - Redirect PP | 5d | Thu 4/18/19 | Wed 4/24/19 |  |  |  | VI. Test
Amazon Iterative Review | 5d | Thu 4/18/19 | Wed 4/24/19
Amazon Sign Off | 1d | Wed 4/24/19 | Wed 4/24/19
No Self Service (SMF 1.1) - Structured Input & Ticket Creation | 5d | Thu 4/18/19 | Wed 4/24/19 |  | Business Analyst | Varun/Mohan | VI. Test
SMF - Pick Transaction - User and Transaction Rules - Create Ticket | 5d | Thu 4/18/19 | Wed 4/24/19 |  | Business Analyst | Varun/Mohan | VI. Test
Amazon Iterative Review | 5d | Thu 4/18/19 | Wed 4/24/19
Amazon Sign Off | 1d | Wed 4/24/19 | Wed 4/24/19
Configurable Screens and Exceptions | 5d | Thu 4/18/19 | Wed 4/24/19 |  | Business Analyst | Varun/Mohan | VI. Test
Configurable Screen for Self Service URLs | 5d | Thu 4/18/19 | Wed 4/24/19 |  | Development Leads | Siva/Mayuresh/Koteswararao | VI. Test
Escape Valve | 5d | Thu 4/18/19 | Wed 4/24/19 |  | Business Analyst | Varun/Mohan | VI. Test
Amazon Iterative Review | 5d | Thu 4/18/19 | Wed 4/24/19
Amazon Sign Off | 1d | Wed 4/24/19 | Wed 4/24/19
QA testing & Performance - Capacity Testing | 5d | Wed 4/24/19 | Wed 5/1/19 | 929
Redirect to Self Service Portal (SMF 1.0) | 5d | Thu 4/25/19 | Wed 5/1/19 |  | Digital PM/Project PM | Mohan/Ken | VI. Test
SMF - Pick Transaction - User and Transaction Rules - Redirect PP | 5d | Thu 4/25/19 | Wed 5/1/19 |  |  |  | VI. Test
Personal Details - Self Service | 5d | Thu 4/25/19 | Wed 5/1/19 |  | Business Analyst | Varun/Mohan | VI. Test
Address - Contact Details - Disability - Emergency Contact - Ethnicity - Gender - Preferred Name - Vetran info | 5d | Thu 4/25/19 | Wed 5/1/19 |  | Business Analyst | Varun/Mohan | VI. Test
Job Data - Self Service | 5d | Thu 4/25/19 | Wed 5/1/19 |  | Business Analyst | Varun/Mohan | VI. Test
Business Title - Company - Department - FCLM Area and FCLM job - Full Time - Part Time - Pay Group - Product Line - Shift Pattern and ADP shift - Supervisor Change - Transfer | 5d | Thu 4/25/19 | Wed 5/1/19 |  | Business Analyst | Varun/Mohan | VI. Test
Amazon Iterative Review | 5d | Thu 4/25/19 | Wed 5/1/19
Amazon Sign Off | 1d | Wed 5/1/19 | Wed 5/1/19
No Self Service (SMF 1.1) - Structured Input & Ticket Creation | 5d | Thu 4/25/19 | Wed 5/1/19 |  | Business Analyst | Varun/Mohan | VI. Test
Amazon Iterative Review | 5d | Thu 4/25/19 | Wed 5/1/19
Amazon Sign Off | 1d | Wed 5/1/19 | Wed 5/1/19
Configurable Screens and Exceptions | 5d | Wed 4/24/19 | Wed 5/1/19 |  | Business Analyst | Varun/Mohan | VI. Test
Configurable Screen for Self Service URLs | 5d | Thu 4/25/19 | Wed 5/1/19 |  | Development Leads | Siva/Mayuresh/Koteswararao | VI. Test
Redirect to Self Service | 5d | Thu 4/25/19 | Wed 5/1/19 |  | Development Leads | Siva/Mayuresh/Koteswararao | VI. Test
No Self Service | 5d | Thu 4/25/19 | Wed 5/1/19 |  | Development Leads | Siva/Mayuresh/Koteswararao | VI. Test
Escape Valve | 5d | Thu 4/25/19 | Wed 5/1/19 |  | Business Analyst | Varun/Mohan | VI. Test
QA Testing | 3d | Thu 4/25/19 | Mon 4/29/19 | 1004994
Performance & Capacity Testing | 5d | Wed 4/24/19 | Wed 5/1/19 |  |  | Rajesh Bachala
Amazon Iterative Review | 5d | Thu 4/25/19 | Wed 5/1/19
Amazon Sign Off | 1d | Wed 5/1/19 | Wed 5/1/19
UAT Handover to Amazon | 10d | Thu 5/2/19 | Wed 5/15/19 | 1007 | QA Lead | Rajesh Bachala | VI. Test
Functional Testing | 10d | Thu 5/2/19 | Wed 5/15/19 | 1048
Perform user Acceptance Testing (UAT) | 10d | Thu 5/2/19 | Wed 5/15/19
Resolve UAT severity defects phase 1 | 10d | Thu 5/2/19 | Wed 5/15/19 |  | Developer / Business Analyst | LTI /Ahbi/Anand | VI. Test
Hold UAT testing go - no-go | 1d | Thu 5/2/19 | Thu 5/2/19 |  | APS PM | Malissaf | VI. Test
Regression Testing | 10d | Thu 5/2/19 | Wed 5/15/19
Perform technical regression testing | 10d | Thu 5/2/19 | Wed 5/15/19 |  | QA Lead | Rajesh Bachala | VI. Test
<New Summary Task> | 10d | Thu 5/2/19 | Wed 5/15/19
Perform business regression testing | 10d | Thu 5/2/19 | Wed 5/15/19 |  | Business Analyst / Support Analyst | Ahbi/Anand | VI. Test
Hold go - no-go meeting to go live | 1d | Thu 5/16/19 | Thu 5/16/19 | 1059 | APS PM | Malissaf | VI. Test
DEPLOY | 7d | Fri 5/17/19 | Mon 5/27/19 | 1068
Execute business cutover plan phase | 5d | Fri 5/17/19 | Mon 5/27/19 |  | HR Services PM | agnitin | VII. Deploy
Execute communications plan | 5d | Fri 5/17/19 | Thu 5/23/19 |  | HR Services PM | agnitin | VII. Deploy
Execute learning plan | 5d | Fri 5/17/19 | Thu 5/23/19 |  | HR Services PM | agnitin | VII. Deploy
Execute prod support and warranty plan | 5d | Fri 5/17/19 | Thu 5/23/19 |  | Support Analyst | LTI | VII. Deploy
Production Go Live | 1d | Thu 5/23/19 | Thu 5/23/19 |  | APS PM | Malissaf | VI. Test
STABILIZE - CLOSE | 10d | Fri 5/24/19 | Thu 6/6/19 | 1074
Update Business and Project Artifacts from Solution Validation | 10d | Fri 5/24/19 | Thu 6/6/19
Update process, SOP, and knowledge based on test results | 10d | Fri 5/24/19 | Thu 6/6/19 |  | HR Services | agnitin | VI. Test
Update learning and communication plans based on test results | 10d | Fri 5/24/19 | Thu 6/6/19 |  | HR Services PM | agnitin | VI. Test
Execute benefits realization monitoring plan | 10d | Fri 5/24/19 | Thu 6/6/19 |  | HR Services PM | agnitin | VIII. Stabilize/Close
Execute VoC feedback plan | 10d | Fri 5/24/19 | Thu 6/6/19 |  | HR Services PM | agnitin | VIII. Stabilize/Close
Perform knowledge transfer from project team to Prod Support | 10d | Fri 5/24/19 | Thu 6/6/19 |  | Support Analyst | LTI | VIII. Stabilize/Close
Perform knowledge transfer from project team to HR Services | 10d | Fri 5/24/19 | Thu 6/6/19 |  | HR Services PM | agnitin | VIII. Stabilize/Close
Complete Warranty Commit | 10d | Mon 5/27/19 | Fri 6/7/19 | 1074 | APS PM | Malissaf | VII. Deploy
Gain agreement to handoff project to customer | 2d | Mon 6/10/19 | Tue 6/11/19 | 1083 | APS PM | Malissaf | VIII. Stabilize/Close
Release project team | 1d | Mon 6/10/19 | Mon 6/10/19 |  | APS PM | Malissaf | VIII. Stabilize/Close
Conduct lessons learned | 2d | Mon 6/10/19 | Tue 6/11/19 |  | APS PM | Malissaf | VIII. Stabilize/Close
Close all tasks in Project Center and upload final docs | 2d | Mon 6/10/19 | Tue 6/11/19 |  | APS PM | Malissaf | VIII. Stabilize/Close